## Sheet1
Action | Responsible for | Allocated family | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | ARRIVAL DAY | Day 1 | Day 2 | Day 3 | Week 1 | Week 2 | Week 3 | Week 4 | Month 1 | Month 2 | Month 3 | Month 4
Notify GP | bar: Week 1 to Week 2
Book JCP appointment | bar: Day 1 to Day 3
Register at schools | bar: Week 1 to Week 2
Prepare accomodation
Organise 24hr interpreters for week 1 | bar: Week 1
Decide who collects from airport
Arrange transport
Pass on BRP | bar: Day 1 to Week 1
Discuss Tenancy Agreement | bar: Week 1
Discuss bills and budgeting | bar: Day 2
Discuss Empowerment
Goal Setting | bar: Week 3 to Week 4
Home Office Reviews | bar: Month 1; Month 4